## Sheet2
Task Name | Duration | Start | Finish | Predecessors | Resource Names | % Complete
BOM Interface | 50 days | Thu 8/11/22 | Thu 10/20/22 |  |  | 8%
Requirement Gathering | 1 day | Thu 8/11/22 | Thu 8/11/22 |  | Hatami | 100%
Application Development | 42 days | Fri 8/12/22 | Tue 10/11/22 |  |  | 7%
Application Mockup | 5 days | Fri 8/12/22 | Fri 8/19/22 | 2 | Hatami | 50%
Database Design | 1 day | Mon 8/22/22 | Mon 8/22/22 | 4 | Hatami | 0%
Master Data | 5 days | Tue 8/23/22 | Mon 8/29/22 | 5 | Hatami | 0%
Role | [5 empty] | 0%
User | [5 empty] | 0%
Plant | [5 empty] | 0%
Setting | [5 empty] | 0%
BOM Usage | [5 empty] | 0%
BOM Status | [5 empty] | 0%
Item Category | [5 empty] | 0%
Costing Relevancy | [5 empty] | 0%
BOM Type | [5 empty] | 0%
Matrix Approval By Plant | [5 empty] | 0%
Authentication By User ID | 1 day | Tue 8/30/22 | Tue 8/30/22 | 6 | Hatami | 0%
Dashboard | 5 days | Wed 8/31/22 | Tue 9/6/22 | 17 | Hatami | 0%
Main form CRUD | 5 days | Wed 9/7/22 | Tue 9/13/22 | 18 | Hatami | 0%
Approval - Approve, Revise, Reject | 5 days | Wed 9/14/22 | Tue 9/20/22 | 19 | Hatami | 0%
Printing PDF | 2 days | Wed 9/21/22 | Thu 9/22/22 | 20 | Hatami | 0%
Email Notification | 3 days | Fri 9/23/22 | Tue 9/27/22 | 21 | Hatami | 0%
SAP Integration | 10 days | Wed 9/28/22 | Tue 10/11/22 |  |  | 0%
Generate CSV Base on Template | 3 days | Wed 9/28/22 | Fri 9/30/22 | 22 | Hatami | 0%
Job Scheduler get CSV From SAP | 2 days | Mon 10/3/22 | Tue 10/4/22 | 24 | Hatami | 0%
Create Resend Page | 2 days | Wed 10/5/22 | Thu 10/6/22 | 25 | Hatami | 0%
Testing | 2 days | Fri 10/7/22 | Mon 10/10/22 | 26 | All | 0%
Bugs Fixing | 1 day | Tue 10/11/22 | Tue 10/11/22 | 27 | Hatami | 0%
Deployment Testing | 1 day | Wed 10/12/22 | Wed 10/12/22 | 28 | Hatami | 0%
Internal Testing | 1 day | Thu 10/13/22 | Thu 10/13/22 | 29 |  | 0%
UAT | 1 day | Fri 10/14/22 | Fri 10/14/22 | 30 | All | 0%
Bugs Fixing | 2 days | Mon 10/17/22 | Tue 10/18/22 | 31 | Hatami | 0%
Deployment Production | 1 day | Wed 10/19/22 | Wed 10/19/22 | 32 |  | 0%
Technical Documentation | 1 day | Thu 10/20/22 | Thu 10/20/22 | 33 | Hatami | 0%